## Sheet1
Start date	10.01.2009
End date	31.08.2009
Publish date	31.09.2009

Task	Hours
Project setup	12		3
Model	8
Adm. Registration/login	12
Adding organization	6
Permission levels	4
Routes	40
Discounts	8
Other settings	4
Mark seat as used	18
Ticket template	8
Printing ticket (jasper)	6
Travel list	2
Statistics	12
Desktop app	2
SMS notification	2

User registration/login/profile	12
Search	16
Travel history	6
Buying & printing ticket	36
Payment	12

Unique identifier	2

Activating organizations	2
Tracking payments	6
Invoicing	6
Statistics	6

Overhead	20.00%

Total	248

Work rate	20	Hours / week
Weeks	12.4